## Sheet1
Stupid Robot Flash Wish List |  |  |  |  | High Priority | High Priority - Reliant on Artists
[5 empty] | Artist Stuff | Low Priority
Status | Name | Date | Job |  | Done | REALLy FUCKING IMPORTANT
GENERAL
we need looping music
we need to determine locations for where we want an "enter saved code" and "get save code", or possibly have the save code be visible during viewscore as well
DEVLOGOSTATE
DONE | Dave | 2009-05-20 | new developer logo needs to be implemented
DONE | Tom | 2009-05-21 | mouse click needs to skip to next logo
DONE | Dave | 2009-05-20 | logos should be in three timered events/movieclips
potentially add side to side animation of an army of brains marching across the screen before the logo fades in and out
new publisher logo needs to be designed
new game logo needs to be designed
new publisher logo needs to be implemented
new game logo needs to be implemented
for some strange reason it isn't loading the new clips at their first animation frame…
MAIN MENU
DONE | Dave | 2009-05-22 | start new game state
DONE | Tom | 2009-05-20 | profile management button needs to be removed from main menu
DONE | Gio | 2009-05-24 | Menu backgrounds general art
DONE | Dave | 2009-05-24 | main menu background implemented
load game button needs to launch a loadgame state
CREDITSSTATE
DONE | Dave | 2009-05-22 | mousclick anywhere should have the effect of hitting esc/~
possibly have some sort of animation going on here, potentially add colors and whatnot as well, the whole state is kinda plain
LOADGAMESTATE
text field needed to be added for typing in encrypted player data
error checking for if invalid data is entered and prompt to put in new data
encryption/decryption of player data to a form of hash data needs to be implemented
if data is ok, decrypt data, load to memory, launch level select state
HELPSCREENSTATE
DONE | Tom | 2009-05-20 | help screen needs a background
DONE | Tom | 2009-05-20 | text for tiles needs to be added
DONE | Tom | 2009-05-20 | instructions need description
text/art needs to be updated for each page for aesthetics
hovers for tiles needs to be added
click on a tile should launch a popup window thing showing an animation of that tile being used
hover for instructions needs to be added
click on an instruction should launch a popup window thing showing an animation of that instruction being used
UI Diagram needs to be updated
QUIT
DONE | Dave | 2009-05-22 | once final game is up, quit needs to point to the game's homepage and not to porn
START NEW GAME
DONE |  | 2009-05-22 | needs to default to level 1
DONE | Dave | 2009-05-22 | needs to prompt for player name…
PLAYGAMESTATE
DONE | Tom | 2009-05-21 | level skipping needs to be re-introduced for debugging purposes
DONE | Tom | 2009-05-21 | level select - debug should be implemented that allows selecting a level from the full list
DONE | Tom | 2009-05-20 | skip this tutorial button needs to be implemented
LOGICINTERFACE
DONE | Dave | 2009-05-22 | pregame needs mouseclick to skip the pregame
DONE | corwin | 2009-05-20 | Sub-routine buttons
DONE | Corwin | 2009-05-20 | Sub-routine Implementation
DONE | Corwin | 2009-05-20 | Black-out Unavailable Commands
DONE | Corwin | 2009-05-20 | Ensure Correct Values for LogicBlock loading in GameVars
DONE | Corwin | 2009-05-22 | insertion inserts stuff on the top 3 rows, no matter how far scrolled down you are
DONE | Corwin | 2009-05-22 | Stop triggers an abort
DONE | Dave | 2009-05-23 | click-hold for all compass elements
DONE | Corwin | 2009-05-23 | instruction hovering remains popped up even when you aren't hovering on stuff
DONE | Corwin | 2009-05-23 | instruction hovering text doesn't wrap at all… like not even a little tiny tiny bit
DONE | Corwin | 2009-05-24 | Command Highlighting
DONE | Dave | 2009-05-24 | make hover tip movieclip match the overall art style
DONE | Evan/Dave | 2009-05-24 | art for instructions
DONE | Dave | 2009-05-24 | cleanup of ui in general
DONE | Evan | 2009-05-24 | execute button art
DONE | Evan | 2009-05-24 | reset button art
DONE | Evan | 2009-05-24 | clear button art
DONE | Evan | 2009-05-24 | help button art
DONE | Corwin | 2009-05-24 | reset button should clear out highlighted command
DONE | Corwin | 2009-05-24 | reset button should bring you back to main
DONE | Corwin | 2009-05-24 | insertion black line needs to be fixed properly to tiles
DONE | Evan | 2009-05-26 | art for move forward until unable
art for tiles
art for robot
inside the funciton resetexecutionmode is causing an error
Sub routines need to have some kind of an indicator as to which one is selected.
PLAYGAME/GAMEBOARD
DONE | Tom | 2009-05-21 | on death needs to have a text popup saying you died
DONE | Tom | 2009-05-21 | on death maybe zoom way in on the robot to show the death animation
DONE | Tom | 2009-05-21 | on death needs to fire abort
DONE | Dave | 2009-05-22 | dying to an electric wall needs a sound
DONE | Dave | 2009-05-22 | jumping into an electric wall needs to kill you instead of jumping you through it from 1 square away
DONE | Dave | 2009-05-22 | jumping into an electric wall while standing on that wall needs to play a death sound
DONE | Dave | 2009-05-22 | teleportCheck() is erroring "A term is undefined and has no properties", possibly if there's no teleporters on the map, not really sure
DONE | Tom | 2009-05-22 | since we have no "esc" key for flash, we need a menu button to bring up the ingame options screen
DONE | Dave | 2009-05-22 | since we have no "esc" key for flash, we need single mouse click to skip through pregame
DONE | Dave | 2009-05-22 | multiple boards are being loaded/etc from level select stuff
DONE | Dave | 2009-05-23 | subroutines need to work
DONE | Dave | 2009-05-24 | add a background to gameplay
DONE | Dave | 2009-05-24 | min zoom needs to be a higher zoom - gameboard line 399 - 0.6
DONE | Dave | 2009-05-24 | default zoom needs to be a higher zoom gameboard line 2239 - 1.45
DONE | Dave | 2009-05-24 | max zoom - 3.45
DONE | Evan | 2009-05-26 | post game screen art
DONE | Evan | 2009-05-26 | replay level button art
DONE | Evan | 2009-05-26 | exit button art
DONE | Evan | 2009-05-26 | advance button art
DONE | Evan | 2009-05-26 | pregame screen needs a new background
"sometimes" teleporters aren't firing properly, really hard to reproduce
why in the hell does the game lag as you play more and more?
pregame bytes available doesn't work right on first level load, make sure level is done loading before displaying stuff
gameboard initial zoom is not being set to reset zoom values
if you hit skip tutorial… have it clear the instruction list
OPTIONS STATE
DONE | Tom | 2009-05-20 | movie clip needs to be added to stage and buttons implemented
DONE | Tom | 2009-05-20 | return to main menu needs to be impleneted
DONE | Tom | 2009-05-20 | return to game needs to be implemented
DONE | Tom | 2009-05-20 | quit needs to launch to company page
DONE | Tom | 2009-05-20 | help needs to bring up help screen
DONE | Tom | 2009-05-21 | Skip all tutorial levels needs to be implemented
Return to main menu doesn't get rid of the gameboard, should fire something like delete all other states or something
GAMEOVER
we need a beat the game video
HIGHSCORES
maybe a web based form that allows you to enter your name and a code and keeps track/shows your high scores and whatnot
Dana Things
DONE | Dave | 2009-05-22 | Dswitch - Switches that can toggle the tile type from one type to another
DONE | Dave | 2009-05-22 |  | Will need to read in with the switch as well as the alternate type
DONE | Dave | 2009-05-22 | The ability for tiles to start off inactive
Level Select State
DONE | Tom | 2009-05-22 | needs to allow select increment
DONE | Tom | 2009-05-22 | needs to allow select decrement
DONE | Tom | 2009-05-22 | needs to allow selection of map
DONE | Dave | 2009-05-22 | map previews
DONE | Tom | 2009-05-22 | exit button implementation
DONE | Universal | 2009-05-24 | map preview glitch for a second showing original size, I can't figure out what's causing this… anyone want to take a look at this?
Nifty Shit
skip this level allowable x # of times
solve this level
multi-color stuff for not available, bytes used, etc, etc
Gamestate manager
DONE | Dave | 2009-05-24 | gamestate manager needs to set the top state to active
Sounds
complete sound overhaul
Art to update to the current state
DONE | Dave | 2009-05-24 | credits
DONE | Dave | 2009-05-24 | pregame
DONE | Dave | 2009-05-24 | view score
DONE | Dave | 2009-05-24 | level select - fit to screen
FIX ERRORS GOD DAMMIT