## wish list
Stupid Robot Flash Wish List |  |  |  |  | High Priority | High Priority - Reliant on Artists
[5 empty] | Artist Stuff | Low Priority
Status | Name | Date | Job |  | Done | REALLy FUCKING IMPORTANT
DONE
DONE | Dave | 2009-05-20 | new developer logo needs to be implemented
DONE | Dave | 2009-05-20 | logos should be in three timered events/movieclips
DONE | Tom | 2009-05-20 | profile management button needs to be removed from main menu
DONE | Tom | 2009-05-20 | help screen needs a background
DONE | Tom | 2009-05-20 | text for tiles needs to be added
DONE | Tom | 2009-05-20 | instructions need description
DONE | Tom | 2009-05-20 | skip this tutorial button needs to be implemented
DONE | corwin | 2009-05-20 | Sub-routine buttons
DONE | Corwin | 2009-05-20 | Sub-routine Implementation
DONE | Corwin | 2009-05-20 | Black-out Unavailable Commands
DONE | Corwin | 2009-05-20 | Ensure Correct Values for LogicBlock loading in GameVars
DONE | Tom | 2009-05-20 | movie clip needs to be added to stage and buttons implemented
DONE | Tom | 2009-05-20 | return to main menu needs to be impleneted
DONE | Tom | 2009-05-20 | return to game needs to be implemented
DONE | Tom | 2009-05-20 | quit needs to launch to company page
DONE | Tom | 2009-05-20 | help needs to bring up help screen
DONE | Tom | 2009-05-21 | mouse click needs to skip to next logo
DONE | Tom | 2009-05-21 | level skipping needs to be re-introduced for debugging purposes
DONE | Tom | 2009-05-21 | level select - debug should be implemented that allows selecting a level from the full list
DONE | Tom | 2009-05-21 | on death needs to have a text popup saying you died
DONE | Tom | 2009-05-21 | on death maybe zoom way in on the robot to show the death animation
DONE | Tom | 2009-05-21 | on death needs to fire abort
DONE | Tom | 2009-05-21 | Skip all tutorial levels needs to be implemented
DONE | Dave | 2009-05-22 | start new game state
DONE | Dave | 2009-05-22 | mousclick anywhere should have the effect of hitting esc/~
DONE | Dave | 2009-05-22 | once final game is up, quit needs to point to the game's homepage and not to porn
DONE | Tom | 2009-05-22 | needs to default to level 1
DONE | Dave | 2009-05-22 | needs to prompt for player name…
DONE | Dave | 2009-05-22 | pregame needs mouseclick to skip the pregame
DONE | Corwin | 2009-05-22 | insertion inserts stuff on the top 3 rows, no matter how far scrolled down you are
DONE | Corwin | 2009-05-22 | Stop triggers an abort
DONE | Dave | 2009-05-22 | dying to an electric wall needs a sound
DONE | Dave | 2009-05-22 | jumping into an electric wall needs to kill you instead of jumping you through it from 1 square away
DONE | Dave | 2009-05-22 | jumping into an electric wall while standing on that wall needs to play a death sound
DONE | Dave | 2009-05-22 | teleportCheck() is erroring "A term is undefined and has no properties", possibly if there's no teleporters on the map, not really sure
DONE | Tom | 2009-05-22 | since we have no "esc" key for flash, we need a menu button to bring up the ingame options screen
DONE | Dave | 2009-05-22 | since we have no "esc" key for flash, we need single mouse click to skip through pregame
DONE | Dave | 2009-05-22 | multiple boards are being loaded/etc from level select stuff
DONE | Dave | 2009-05-22 | Dswitch - Switches that can toggle the tile type from one type to another
DONE | Dave | 2009-05-22
DONE | Dave | 2009-05-22 | The ability for tiles to start off inactive
DONE | Tom | 2009-05-22 | needs to allow select increment
DONE | Tom | 2009-05-22 | needs to allow select decrement
DONE | Tom | 2009-05-22 | needs to allow selection of map
DONE | Dave | 2009-05-22 | map previews
DONE | Tom | 2009-05-22 | exit button implementation
DONE | Dave | 2009-05-23 | click-hold for all compass elements
DONE | Corwin | 2009-05-23 | instruction hovering remains popped up even when you aren't hovering on stuff
DONE | Corwin | 2009-05-23 | instruction hovering text doesn't wrap at all… like not even a little tiny tiny bit
DONE | Dave | 2009-05-23 | subroutines need to work
DONE | Gio | 2009-05-24 | Menu backgrounds general art
DONE | Dave | 2009-05-24 | main menu background implemented
DONE | Corwin | 2009-05-24 | Command Highlighting
DONE | Dave | 2009-05-24 | make hover tip movieclip match the overall art style
DONE | Evan/Dave | 2009-05-24 | art for instructions
DONE | Dave | 2009-05-24 | cleanup of ui in general
DONE | Evan | 2009-05-24 | execute button art
DONE | Evan | 2009-05-24 | reset button art
DONE | Evan | 2009-05-24 | clear button art
DONE | Evan | 2009-05-24 | help button art
DONE | Corwin | 2009-05-24 | reset button should clear out highlighted command
DONE | Corwin | 2009-05-24 | reset button should bring you back to main
DONE | Corwin | 2009-05-24 | insertion black line needs to be fixed properly to tiles
DONE | Dave | 2009-05-24 | add a background to gameplay
DONE | Dave | 2009-05-24 | min zoom needs to be a higher zoom - gameboard line 399 - 0.6
DONE | Dave | 2009-05-24 | default zoom needs to be a higher zoom gameboard line 2239 - 1.45
DONE | Dave | 2009-05-24 | max zoom - 3.45
DONE | Universal | 2009-05-24 | map preview glitch for a second showing original size, I can't figure out what's causing this… anyone want to take a look at this?
DONE | Dave | 2009-05-24 | gamestate manager needs to set the top state to active
DONE | Dave | 2009-05-24 | credits
DONE | Dave | 2009-05-24 | pregame
DONE | Dave | 2009-05-24 | view score
DONE | Dave | 2009-05-24 | level select - fit to screen
DONE | Evan | 2009-05-26 | art for move forward until unable
DONE | Evan | 2009-05-26 | post game screen art
DONE | Evan | 2009-05-26 | replay level button art
DONE | Evan | 2009-05-26 | exit button art
DONE | Evan | 2009-05-26 | advance button art
DONE | Evan | 2009-05-26 | pregame screen needs a new background
DONE | Cesar | 2009-05-28 | art for tiles
DONE | Dave | 2009-05-29 | reprograms need green on ground too
DONE | Dave | 2009-05-31 | new publisher logo needs to be designed
DONE | Dave | 2009-05-31 | new game logo needs to be designed
DONE | Dave | 2009-05-31 | new publisher logo needs to be implemented
DONE | Dave | 2009-05-31 | new game logo needs to be implemented
DONE | Dave | 2009-05-31 | for some strange reason it isn't loading the new clips at their first animation frame…
DONE | Dave | 2009-05-31 | marching sound should stop when you skip devlogo
DONE | Dave | 2009-05-31 | mr roboto sound added
DONE | Corwin | 2009-05-31 | Sub routines need to have some kind of an indicator as to which one is selected. | Will need to read in with the switch as well as the alternate type
DONE | Dave | 2009-05-31 | level select state must not allow a level to be selected if it isn't finished loading
DONE | Corwin | 2009-05-31 | don't allow map rotation when processing at all
DONE | Dave | 2009-05-31 | electric death animation isn't drawing now for some reason
DONE | Dave | 2009-05-31 | gameboard initial zoom is not being set to reset zoom values
DONE | Corwin | 2009-05-31 | if you hit skip tutorial… have it clear the instruction list
DONE | Corwin | 2009-05-31 | pregame bytes available doesn't work right on first level load, make sure level is done loading before displaying stuff
DONE | Corwin | 2009-05-31 | after you abort, when you execute, the robot doesn't draw immediately, rather it draws after the first execution is processed
DONE | Dave | 2009-05-31 | see if we need to kill the robot in the update
DONE | Dave | 2009-05-31 | level select state images are glitching out
DONE | Dave | 2009-05-31 | pregame needs to not let you click until it finishes loading the map
DONE | Dave | 2009-05-31 | duplicate rebuildmapclips probably inside of loadmapfromfile
DONE | Dave | 2009-05-31 | selectbuttonclic and remove and rebuild are both loading in a map simultaneously
DONE | Tom | 2009-05-31 | Return to main menu doesn't get rid of the gameboard, should fire something like delete all other states or something
DONE | Tom | 2009-05-31 | robot is glitching during jump, showing the robot at the start square then warping to target square
DONE | Tom | 2009-05-31 | robot doesn't work when jumping to the bottom left… why?!
DONE | Tom | 2009-05-31 | robot is thinking it can jump off the board, stupid robot
DONE | Tom | 2009-05-31 | robot dies not come back to life after dying to electricity
DONE | Dave/Tom | 2009-05-31 | robot draw order during jumps needs to be adjusted
DONE | Dave | 2009-05-31 | Activate art needs to be propegated through the tiles and made better in general
DONE | Universal | 2009-06-01 | tiles need color picking
DONE | Jermain/Dave | 2009-06-01 | art for robot
DONE | Tom | 2009-05-31 | any and all setchildindex's should first check to see if the object is already at the spot it should be, if it is, then do nothing
DONE | Dana | 2009-06-01 | write tutorial messages
DONE | Dana | 2009-06-01 | build tutorial map
DONE | Corwin | 2009-06-01 | put tutorial messages into flash
DONE | Corwin | 2009-06-01 | add tutorial tile to gameboard
DONE | Dave | 2009-06-01 | enter on player name entry etc
DONE | Dave | 2009-06-01 | switches need to switch its self art to inactive even if there is no code attached to it
DONE | Dave | 2009-06-01 | fix draw heights of climb tiles
DONE | Dave | 2009-06-01 | help screen pages 2 and 3 need to work again (tiles)
DONE | Dave | 2009-06-01 | jumping down to left needs an extra +1 y or just a +1 overall, not sure, try jumping on mousetrap level right at the start
DONE | Dave | 2009-06-01 | dswitches need to support a 41st tile
DONE | Dave | 2009-06-01 | repgrogram text needs to be green and in the proper location
DONE | Dave | 2009-06-01 | processing switches/dswitches should process at 4x speed of your processing speed
DONE | Dave | 2009-06-01 | speed up jump animations
DONE | Dave | 2009-06-01 | execute needs to not reset the map's rotation
DONE | Dave | 2009-06-01 | make switches slower again
DONE | Dave | 2009-06-02 | as soon as tutorial level pops up, getting an error in tutorialtilecheckandexecution() - needed to wait for the level to finish loading
DONE | Dave | 2009-06-02 | upon arrival from a teleport, robot needs to reinject
DONE | Dave | 2009-06-02 | add error checking for teleporters to make sure that there is an assigned bit of teleport code for it, if not, trace out an error
DONE | Corwin | 2009-06-02 | add tutorial popup state
DONE | Corwin | 2009-06-02 | landing a jump on a tutorial square breaks shit
DONE | Dave | 2009-06-02 | when you click the you died window, make it reset zoom to default
DONE | Dave | 2009-06-02 | once death animation starts running, need to clear out all ui abilities until clicking ok on you died
DONE | Dave | 2009-06-02 | remove tutoriallevel++ from all but the real tutorial level
DONE | Dave | 2009-06-02 | make the info/skip tutorial buttons vanish when you skip past tutorials
REALLY FUCKING IMPORTANT
High Priority
UI Diagram needs to be deleted from help
why in the hell does the game lag as you play more and more?
complete sound overhaul
for final release - make sure level select is clamped
TUTORIAL - button to bring up tutorial text at any time for current status of tutorial progress
TUTORIAL - ability to go backwards in the text reader thingie to see old tutorial info
TUTORIAL - don’t' let them scroll too far etc
new help page - tutorial movieclip
victory dance
if I have time, make sure that all teleporters that can appear via a dswitch have associated code
logic interface should not let you click and drag thingies when it says "you died" on the screen
maps need tobe reordered
maybe include maps inside the swf once they are finalized
High Priority - reliant on art
credits possibly have some sort of animation going on here, potentially add colors and whatnot as well, the whole state is kinda plain
Low Priority
we need looping music
click on a tile should launch a popup window thing showing an animation of that tile being used
click on an instruction should launch a popup window thing showing an animation of that instruction being used
inside the funciton resetexecutionmode is causing an error
skip this level allowable x # of times
solve this level
multi-color stuff for not available, bytes used, etc, etc

## level notes
Level Name | Memory Used
Mouse Trap | 72
Oscar 6 | CANNOT BEAT LEVEL
Oscar 7 | CANNOT BEAT LEVEL
Oscar 8 | 228
Oscar 9 | 318
Oscar 10 | 156